## Rehearsal Schedule
University of Illinois |  |  |  |  | Hyatt Regency Scottsdale Gainey Ranch
THURSDAY, February 28, 2019
# | Time | TRT | Element | A/V | Notes
| 8:00 | 4:00 | Crew call - set-up
| 12:00 | 1:00 | Lunch/teleprompter check
| 13:00 | 2:00 | Set-up continues
| 15:00 | 0:30 | Technical rehearsal
PRESENTER REHEARSALS
| 15:30 | 0:30 | Speaker
| 16:00 | 0:15 | Speaker
| 16:15 | 0:15 | Speaker
| 16:30 | 0:15 | Speaker
| 16:45 | 0:15 | Speaker
| 17:00 | 0:15 | Verify tec knows cues, run through final script
| 17:15 | 0:30 | Rehearsals complete, crew break
| 17:45 |  | Ready for doors to open

## Show Flow Scottsdale
University of Illinois | [5 empty] | VENUE
DATE
# | Time | TRT | Element | Screen | Audio | Notes
| 17:45 |  | Doors open
1 | 18:00 |  | Pre-event Networking | Drone video loop | walk-in music | Preset: 2 music stands
2 | 18:50 |  | Voice of God Mic, "our program will begin in ten minutes." [repeat at 5] |  | VOG | Off stage at AV table
3 | 19:00 | 0:04 | Program Begins First speaker/performer | PPT VIDEO | list AV inputs needed | Remove music stand from stage
4 | 19:04 | 0:04 | Speaker | PPT | list AV inputs needed
5 | 19:08 | 0:03 | Illinois Video | VIDEO
6 | 19:11 | 0:05 | Speaker | PPT | play on rf 4
7 | 19:16 | 0:02 | Video | VIDEO
8 | 19:18 | 0:05 | Speaker | PPT | play-on rf 5
9 | 19:23 | 0:03 | Video | VIDEO
10 | 19:26 | 0:03 | Speaker | PPT | play-on rf 6
11 | 19:29 | 0:03 | Closing | PPT | play on rf 3
12 | 19:32 | 0:28 | Program ends, cocktails and networking continue | repeat from walk-in | walk-in music
13 | 20:00 | 1:00 | Published event end time, likely extend to 9P
14 | 21:00 |  | Event ends